## Planning
| 22.05.17 W1 |  |  |  |  | 29.05.17 W2 |  |  |  |  | 05.06.17 W3 |  |  |  |  | 12.06.17 W4 |  |  |  |  | 19.06.17 W5 |  |  |  |  | 26.06.17 W6 |  |  |  |  | 03.07.17 W7 |  |  |  |  | 10.07.17 W8 |  |  |  |  | 17.07.17 W9 |  |  |  |  | 24.07.17 W10 |  |  |  |  | 31.07.17 W11 |  |  |  |  | 07.08.17 W12 |  |  |  |  | 14.08.17 W13 |  |  |  |  | 21.08.17 W14 |  |  |  |  | 28.08.17 W15 |  |  |  |  | 04.09.17 W16
Administration | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F
Define project's goal | [80 empty] | Me | bar: 22.05.17 W1 M to 22.05.17 W1 Tu
Define components used | [80 empty] | Other | bar: 22.05.17 W1 M to 22.05.17 W1 Tu
Define specifications | bar: 22.05.17 W1 M to 22.05.17 W1 W; 22.05.17 W1 F to 29.05.17 W2 F
Hardware Development
Search components
Design electronic circuit
Print electronic circuit
Solder electronic circuit
Test electronic circuit
Software Development
Set up the environnement | bar: 05.06.17 W3 M to 05.06.17 W3 Tu; 26.06.17 W6 Th to 03.07.17 W7 M; 17.07.17 W9 M to 17.07.17 W9 Tu
Acquire data | bar: 12.06.17 W4 Th to 19.06.17 W5 W
Transfer data via BLE | bar: 19.06.17 W5 Th to 26.06.17 W6 W
Define scenarios for testing | bar: 05.06.17 W3 W to 05.06.17 W3 F; 03.07.17 W7 Tu to 10.07.17 W8 M
Implementation with Bare Metal | bar: 26.06.17 W6 Th to 10.07.17 W8 F
Implementation with Zephyr | bar: 17.07.17 W9 M to 24.07.17 W10 F
Display the result and save data | bar: 31.07.17 W11 W to 07.08.17 W12 F
Sensor Template | bar: 14.08.17 W13 M to 14.08.17 W13 F
Test
Definition of Criteria
Interruption latency
Power consumption
protocols' requirement
comparison with Bare Metal and Zephyr
Documentation
report | bar: 21.08.17 W14 M to 21.08.17 W14 F
presentation | bar: 28.08.17 W15 M to 28.08.17 W15 Tu
[71 empty] | Reserved |  |  |  |  | Reserved

## Done
| 22.05.17 W1 |  |  |  |  | 29.05.17 W2 |  |  |  |  | 05.06.17 W3 |  |  |  |  | 12.06.17 W4 |  |  |  |  | 19.06.17 W5 |  |  |  |  | 26.06.17 W6 |  |  |  |  | 03.07.17 W7 |  |  |  |  | 10.07.17 W8 |  |  |  |  | 17.07.17 W9 |  |  |  |  | 24.07.17 W10 |  |  |  |  | 31.07.17 W11 |  |  |  |  | 07.08.17 W12 |  |  |  |  | 14.08.17 W13 |  |  |  |  | 21.08.17 W14 |  |  |  |  | 28.08.17 W15 |  |  |  |  | 04.09.17 W16
Administration | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F
Define project's goal | [80 empty] | Me | bar: 22.05.17 W1 M to 22.05.17 W1 Tu
Define components used | [80 empty] | Other | bar: 22.05.17 W1 M to 22.05.17 W1 Tu
Define specifications | bar: 22.05.17 W1 M to 22.05.17 W1 Tu
Hardware Development
Search components
Design electronic circuit
Print electronic circuit
Solder electronic circuit
Test electronic circuit
Software Development
Set up the environnement | bar: 05.06.17 W3 Th to 12.06.17 W4 Tu
Acquire data | bar: 29.05.17 W2 F; 05.06.17 W3 Tu to 05.06.17 W3 F
Transfer data via BLE | bar: 12.06.17 W4 W
Define scenarios for testing
Implementation with Bare Metal
Implementation with Zephyr
Display the result and save data
Sensor Template
Test
Interruption latency
Power consumption
protocols' requirement
comparison with Bare Metal and Zephyr
Documentation
report
presentation
[71 empty] | Reserved |  |  |  |  | Reserved